## Allocation
Task | Owner | Start date | End date | Status
Environment setup (Docker + Paperless-ngx v3.3.0) | Both | 2026-10-10 | 2026-10-10 | Done
Test plan: scope, entry and exit criteria | Azka | 2026-10-10 | 2026-10-11 | Done
Requirement analysis and RTM | Musferah | 2026-10-10 | 2026-10-11 | Done
Test case design: M1 Auth & Users, M2 Documents, M6 Trash & Bulk | Azka | 2026-10-10 | 2026-10-11 | Done
Test case design: M3 Attributes, M4 Search & Saved Views, M5 Workflows | Musferah | 2026-10-10 | 2026-10-11 | Done
Prepare test data files (PDFs, images, empty and large files) | Musferah | 2026-10-10 | 2026-10-10 | Done
Exploratory testing notes | Both | 2026-10-10 | 2026-10-11 | Done
Execution + evidence: M1, M2, M6 | Musferah | 2026-10-11 | 2026-10-12 | Done
Execution + evidence: M3, M4, M5 | Musferah | 2026-10-11 | 2026-10-12 | Done
Defect logging and full defect reports (Appendix B) | Both | 2026-10-11 | 2026-10-12 | Done
Test Summary Report: sections 1-5 | Azka | 2026-10-12 | 2026-10-12 | Done
Test Summary Report: sections 6-9, charts, sign-off | Azka | 2026-10-12 | 2026-10-12 | Done
Evidence index, contribution table, reflection | Both | 2026-10-12 | 2026-10-12 | Done
Viva rehearsal (10-minute walkthrough) | Both | 2026-10-12 | 2026-10-12 | Not Started

## Requirements_RTM
Requirement ID | Module / Feature | Requirement | Priority | Linked Test Cases | # Test Cases | # Passed | # Failed | Coverage
FR-001 | M1 Auth & Users | A user with valid credentials can log in and reaches the dashboard. | High | TC-001 | 1 | 1 | 0 | Covered
FR-002 | M1 Auth & Users | Login with invalid, empty or unknown credentials is refused with a clear error message. | High | TC-002, TC-003, TC-004 | 3 | 3 | 0 | Covered
FR-003 | M1 Auth & Users | Logging out ends the session and protected pages require login again. | High | TC-005 | 1 | 1 | 0 | Covered
FR-004 | M1 Auth & Users | An admin can create users; usernames must be unique and passwords must satisfy the password rules. | High | TC-006, TC-007, TC-008, TC-009 | 4 | 4 | 0 | Covered
FR-005 | M1 Auth & Users | User permissions restrict what a user can view, edit or delete; admins can edit and delete users. | High | TC-010, TC-011, TC-066 | 3 | 2 | 1 | Covered
FR-006 | M2 Documents | Valid documents (PDF, images) uploaded through the web UI are accepted, consumed and listed. | High | TC-012, TC-013, TC-018 | 3 | 3 | 0 | Covered
FR-007 | M2 Documents | Unsupported, empty or invalid files are rejected with a meaningful message and the system keeps working. | High | TC-014, TC-015, TC-016 | 3 | 2 | 0 | Covered
FR-008 | M2 Documents | The system detects duplicate documents. | Medium | TC-017 | 1 | 1 | 0 | Covered
FR-009 | M2 Documents | A user can open a document and see its preview, metadata and extracted content. | Medium | TC-019 | 1 | 1 | 0 | Covered
FR-010 | M2 Documents | A user can edit document metadata (title, dates, ASN); changes persist; ASN must be unique and valid. | High | TC-020, TC-021 | 2 | 2 | 0 | Covered
FR-011 | M2 Documents | A user can download the original and archived versions of a document. | Medium | TC-022 | 1 | 1 | 0 | Covered
FR-012 | M2 Documents | Deleting a document moves it to the trash after confirmation. | High | TC-023 | 1 | 1 | 0 | Covered
FR-013 | M3 Attributes | A user can create tags with a name and colour; the name is required. | High | TC-024, TC-025, TC-027 | 3 | 3 | 0 | Covered
FR-014 | M3 Attributes | Tags can be edited and deleted; names are unique; changes are reflected on all documents. | Medium | TC-026, TC-030, TC-031 | 3 | 3 | 0 | Covered
FR-015 | M3 Attributes | A user can create correspondents with any valid name, including unicode and special characters. | Medium | TC-028 | 1 | 1 | 0 | Covered
FR-016 | M3 Attributes | A user can create document types and assign them to documents. | Medium | TC-029 | 1 | 1 | 0 | Covered
FR-017 | M3 Attributes | A user can create storage paths; invalid or empty paths are rejected. | Medium | TC-032 | 1 | 1 | 0 | Covered
FR-018 | M3 Attributes | A user can create custom fields of each supported data type. | Medium | TC-033, TC-061 | 2 | 1 | 1 | Covered
FR-019 | M3 Attributes | Custom field values are validated against the field's data type. | High | TC-034, TC-062, TC-063, TC-064, TC-065 | 5 | 2 | 3 | Covered
FR-020 | M4 Search & Saved Views | Full-text search returns matching documents and handles no-result and unusual queries safely. | High | TC-035, TC-036, TC-037 | 3 | 3 | 0 | Covered
FR-021 | M4 Search & Saved Views | Documents can be filtered by tag, correspondent, type and date range, alone or combined. | High | TC-038, TC-039, TC-067 | 3 | 2 | 1 | Covered
FR-022 | M4 Search & Saved Views | The document list can be sorted by the available fields in both directions. | Low | TC-040 | 1 | 1 | 0 | Covered
FR-023 | M4 Search & Saved Views | A user can save the current filters and sort order as a saved view. | High | TC-041, TC-042 | 2 | 1 | 1 | Covered
FR-024 | M4 Search & Saved Views | Saved views can be shown on the dashboard and in the sidebar. | Medium | TC-043 | 1 | 1 | 0 | Covered
FR-025 | M4 Search & Saved Views | Saved views can be edited and deleted without affecting documents. | Medium | TC-044 | 1 | 1 | 0 | Covered
FR-026 | M5 Workflows & Matching | A workflow with a consumption trigger applies its actions only to documents matching its filters. | High | TC-051 | 1 | 1 | 0 | Covered
FR-027 | M5 Workflows & Matching | Automatic matching works for each algorithm (any, all, exact, regex) and the case-sensitivity option. | High | TC-045, TC-046, TC-047, TC-048, TC-050 | 5 | 5 | 0 | Covered
FR-028 | M5 Workflows & Matching | An invalid matching pattern (for example a broken regex) is rejected with a clear message. | High | TC-049 | 1 | 1 | 0 | Covered
FR-029 | M5 Workflows & Matching | A workflow can be enabled and disabled; a disabled workflow does not run. | High | TC-052 | 1 | 1 | 0 | Covered
FR-030 | M5 Workflows & Matching | A workflow can be deleted; documents it already processed keep their values. | Medium | TC-053 | 1 | 1 | 0 | Covered
FR-031 | M6 Trash & Bulk Actions | A document can be restored from the trash with its metadata intact. | High | TC-054 | 1 | 1 | 0 | Covered
FR-032 | M6 Trash & Bulk Actions | A document can be permanently deleted from the trash after confirmation. | High | TC-055 | 1 | 1 | 0 | Covered
FR-033 | M6 Trash & Bulk Actions | The trash can be emptied after confirmation. | Medium | TC-056 | 1 | 1 | 0 | Covered
FR-034 | M6 Trash & Bulk Actions | Bulk edit actions (for example adding a tag) apply only to the selected documents. | High | TC-057, TC-058 | 2 | 2 | 0 | Covered
FR-035 | M6 Trash & Bulk Actions | Bulk delete and bulk download act only on the selected documents. | High | TC-059, TC-060 | 2 | 2 | 0 | Covered

## TestCases
Test Case ID | Module / Feature | Linked Requirement ID | Title / Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Severity | Technique | Tester | Execution Date
TC-001 | M1 Auth & Users | FR-001 | Login with valid credentials | Logged out; admin account exists. | 1. Open http://localhost:8000 2. Enter username 3. Enter password 4. Click Sign in | Username: testing; Password: 12345 | User is logged in and lands on the Dashboard showing a greeting with the username. | User is logged in successfully and a greeting message with the user name is showed | Pass | High | Critical | EP | Musferah | 2026-10-10
TC-002 | M1 Auth & Users | FR-002 | Login with correct username and wrong password | Logged out. | 1. Open the login page 2. Enter valid username 3. Enter wrong password 4. Click Sign in | testing / WrongPass#1 | Login is refused with a clear error message; user stays on the login page; no session is created. | login is refused although it didnt specify either the username was incorrect or the password | Pass | High | Major | EP | Musferah | 2026-10-10
TC-003 | M1 Auth & Users | FR-002 | Login with empty username and password | Logged out. | 1. Open the login page 2. Leave both fields empty 3. Click Sign in | Username: (empty); Password: (empty) | Login is refused with a validation message; no error page or crash. | field is required error message shown | Pass | Medium | Minor | BVA, EG | Musferah | 2026-10-10
TC-004 | M1 Auth & Users | FR-002 | Login with a non-existent username | Logged out. | 1. Open the login page 2. Enter an unknown username and any password 3. Click Sign in | nouser123 / Test@12345 | Login is refused with a clear error message. | login is refused | Pass | Medium | Minor | EP | Musferah | 2026-10-10
TC-005 | M1 Auth & Users | FR-003 | Logout ends the session | Logged in. | 1. Click the username menu, choose Logout 2. Press the browser Back button 3. Open http://localhost:8000/documents directly | n/a | User is returned to the login page; Back and the direct URL do not show protected content until logging in again. | user and signed out and the integrity of the data is maintained | Pass | High | Major | ST | Musferah | 2026-10-10
TC-006 | M1 Auth & Users | FR-004 | Admin creates a user with valid details | Logged in as admin. | 1. Open Settings > Users & Groups 2. Click Create 3. Fill in username and password 4. Save 5. Log in as the new user in a private window | Username: testing2; Password: Str0ng!Pass#2026 | User is created, appears in the user list and can log in. | the user is created and can login with the correct credentials | Pass | High | Major | EP | Musferah | 2026-10-11
TC-007 | M1 Auth & Users | FR-004 | Password length boundary when creating a user | Logged in as admin. | 1. Create a user with a 7-character password 2. Create a user with an 8-character password | 7 chars: Ab1!xyz; 8 chars: Ab1!xyz9 | The 7-character password is rejected with a message about minimum length; the 8-character password is accepted. | the user is created with the 8 character password and not with the 7 character password | Pass | Medium | Major | BVA | Musferah | 2026-10-11
TC-008 | M1 Auth & Users | FR-004 | Create user with common or all-numeric password | Logged in as admin. | 1. Create a user with password 12345678 2. Create a user with password password | 12345678; password | Both passwords are rejected with a message, consistent with the validator shown by the createsuperuser command. | both passwords are rejected stating the entirely numeric and too common validators | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-009 | M1 Auth & Users | FR-004 | Create user with a duplicate username | User testing exists. | 1. Create another user named testing 2. Save | Username: testing | Creation is rejected with a clear 'already exists' style message; no duplicate user is created. | the user creation is rejected with proper user already exsist error | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-010 | M1 Auth & Users | FR-005 | Permission matrix: view / edit / delete rights | Admin logged in; at least 3 documents exist. | 1. Create 4 users with these permission sets on documents: view only; view+edit; view+delete; no permissions 2. Log in as each user 3. Try to view, edit and delete a document | Permission sets: V / V+E / V+D / none | Each user can perform only the actions their permissions allow; blocked actions are hidden or denied with a message. | each user performs only the permitted action and the ui changes accordingly | Pass | High | Critical | DT | Musferah | 2026-10-11
TC-011 | M1 Auth & Users | FR-005 | Edit and delete a user | User tester01 exists. | 1. Edit tester01's email and save 2. Delete tester01 3. Try logging in as tester01 | Email: tester01@example.com | Edit is saved; deleted user disappears from the list and can no longer log in. | the user is deleted and is not able to login | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-012 | M2 Documents | FR-006 | Upload a valid PDF | Logged in; sample.pdf prepared (1-page text PDF). | 1. Click Upload documents 2. Select sample.pdf 3. Wait for processing | sample.pdf | Upload succeeds with a notification; the document appears in Documents with extracted title and content. | the documents uploads successfully with the progressive bar | Pass | High | Critical | EP | Azka | 2026-10-11
TC-013 | M2 Documents | FR-006 | Upload JPG and PNG images | Logged in; sample.jpg and sample.png prepared (images containing text). | 1. Upload sample.jpg 2. Upload sample.png 3. Open each document | sample.jpg, sample.png | Both images are consumed and listed; text is extracted into the content tab. | both png and jpg/jpeg formats are supported and the text is extracted in the contents tab | Pass | Medium | Major | EP | Azka | 2026-10-11
TC-014 | M2 Documents | FR-007 | Upload an unsupported file type | Logged in. | 1. Upload tool.exe 2. Upload fake.pdf (an .exe renamed to .pdf) 3. Check notifications and the document list | tool.exe; fake.pdf | Files are rejected or fail with a meaningful message; nothing invalid appears as a document; the app keeps working. | the docx format is not supported and shows the error | Pass | High | Major | EP, EG | Azka | 2026-10-11
TC-015 | M2 Documents | FR-007 | Upload an empty (0 KB) file | Logged in; empty.pdf with size 0 KB. | 1. Upload empty.pdf 2. Check notifications and the document list | empty.pdf (0 KB) | The file is rejected with a meaningful message; no crash and no blank document created. | it shows the submitted file is empty error | Pass | Medium | Minor | BVA | Azka | 2026-10-11
TC-016 | M2 Documents | FR-007 | Upload a very large file | Logged in; large.pdf of 50 MB or more. | 1. Upload large.pdf 2. Watch the upload and the notifications | large.pdf (50 MB+) | The file is either processed successfully or rejected with a clear size message; the UI stays responsive. | this much large pdf isnt available for us | Blocked | Medium | Minor | BVA | Azka | 2026-10-11
TC-017 | M2 Documents | FR-008 | Upload the same document twice | sample.pdf already uploaded. | 1. Upload sample.pdf a second time 2. Check notifications and the document list | sample.pdf | The re-uploaded duplicate is detected and flagged on the document (Duplicates tab). This Paperless version consumes the file rather than rejecting it. | the new official document says the duplicated files are allowed with the flag and it happens so | Pass | High | Major | EP | Azka | 2026-10-11
TC-018 | M2 Documents | FR-006 | Upload a file with special characters in its name | Logged in. | 1. Rename a PDF to the test name 2. Upload it 3. Open the document | rēport #1 (final) & copy.pdf | Upload succeeds; the title and file name display correctly with no corruption. | the document name accepts the characters and spaces | Pass | Low | Minor | EG | Azka | 2026-10-11
TC-019 | M2 Documents | FR-009 | Open document details and preview | At least one document exists. | 1. Click a document in the list 2. View the preview 3. Open the Content and Metadata tabs | sample.pdf | Preview renders; metadata and extracted content are shown and match the document. | the contents and meta data is shown correctly for the document | Pass | Medium | Major | EP | Azka | 2026-10-11
TC-020 | M2 Documents | FR-010 | Edit title and created date, then save | A document exists. | 1. Open the document 2. Change title and created date 3. Save 4. Refresh the page and check the list | Title: Invoice Oct 2026; Created: 2026-10-10 | Changes are saved, persist after refresh and show in the list. | the changes persists | Pass | High | Major | EP | Azka | 2026-10-11
TC-021 | M2 Documents | FR-010 | Archive serial number (ASN): boundaries and uniqueness | At least two documents exist. | 1. Set ASN 0 and 1 on document A 2. Set ASN 1 on document B 3. Try ASN -1 4. Try ASN 4294967296 | ASN: 0, 1, 1 (duplicate), -1, 4294967296 | Valid unique values are saved; duplicate, negative and out-of-range values are rejected with a clear message and no server error. | the negative values are rejected alongside the duplicated ones the highest possible accepted value is 4294967295 | Pass | High | Major | BVA, EP | Azka | 2026-10-11
TC-022 | M2 Documents | FR-011 | Download original and archived file | A document exists. | 1. Open the document 2. Click Download (original) 3. Click Download (archived), if offered 4. Open both files | sample.pdf | Files download and open correctly; content matches the document. | Both documents opens correctly | Pass | Medium | Major | EP | Azka | 2026-10-11
TC-023 | M2 Documents | FR-012 | Delete a document moves it to the trash | A document exists. | 1. Select the document 2. Click Delete and confirm 3. Open the Trash page | sample.pdf | A confirmation is shown; the document leaves the list and appears in Trash; it is not permanently deleted. | the file is shown in trash and removed from the list | Pass | High | Major | ST | Azka | 2026-10-11
TC-024 | M3 Attributes | FR-013 | Create a tag with a valid name and colour | Logged in. | 1. Open Attributes > Tags 2. Click Create 3. Enter name and choose a colour 4. Save | Name: Invoices; Colour: green | Tag is created, listed and selectable on documents. | tag is created successfully and is selectable on the document | Pass | High | Major | EP | Musferah | 2026-10-11
TC-025 | M3 Attributes | FR-013 | Create a tag with an empty name | Logged in. | 1. Open Create tag 2. Leave the name empty 3. Click Save | Name: (empty) | Save is blocked with a clear 'name required' message. | name required error is shown | Pass | Medium | Minor | EP, BVA | Musferah | 2026-10-11
TC-026 | M3 Attributes | FR-014 | Create a tag with a duplicate name | Tag 'Invoices' exists. | 1. Create a tag named Invoices 2. Create a tag named invoices (lowercase) | Invoices; invoices | The exact duplicate is rejected with a clear message. Names are compared case-sensitively, so a name differing only in letter case is accepted. | the case sensitivity persists | Pass | Medium | Major | EP, EG | Musferah | 2026-10-11
TC-027 | M3 Attributes | FR-013 | Tag name length boundary | Logged in. | 1. Create a tag with a 1-character name 2. Create a tag with a 128-character name 3. Create a tag with a 300-character name | 1 char: A; 128 chars; 300 chars | 1 character is accepted; very long names are accepted or rejected with a clear message; there is never a server error. | no more then 128 characters are accepted | Pass | Low | Minor | BVA | Musferah | 2026-10-11
TC-028 | M3 Attributes | FR-015 | Create a correspondent with unicode and special characters | Logged in. | 1. Open Attributes > Correspondents 2. Create each name below 3. Check the list and a document using it | Müller & Söhne <GmbH>; علی ٹریڈرز; O'Brien "Ltd" | All names are saved and displayed exactly as typed with no escaping errors. | All names are saved respectively | Pass | Medium | Minor | EG | Musferah | 2026-10-11
TC-029 | M3 Attributes | FR-016 | Create a document type and assign it to a document | A document exists. | 1. Create document type 'Invoice' 2. Open a document and set its type 3. Filter the list by that type | Type: Invoice | Type is created and assigned; the filter shows the document. | the filter is showing the file according to the document type | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-030 | M3 Attributes | FR-014 | Rename a tag and check the documents | A tag is assigned to a document. | 1. Edit the tag name to Invoices 2026 2. Save 3. Open the document and the document list | New name: Invoices 2026 | The new name shows on every document that has the tag; the document count is unchanged. | the document with the new tag is filtered with the new name | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-031 | M3 Attributes | FR-014 | Delete a tag that is assigned to documents | A tag is assigned to at least two documents. | 1. Delete the tag and confirm 2. Open the affected documents | Tag: Invoices 2026 | Confirmation is shown; the tag is removed from all documents; the documents themselves remain. | the document remains without any effect after the tag is deleted | Pass | High | Major | ST | Musferah | 2026-10-11
TC-032 | M3 Attributes | FR-017 | Storage path with valid, invalid and empty paths | Logged in. | 1. Create a path using the placeholder syntax shown in the UI 2. Try a path with an unknown placeholder 3. Try an empty path | Valid: {{ correspondent }}/{{ title }}; Invalid: {{ nonexistent_var }}; Empty | The valid path is saved; the invalid and empty paths are rejected with a clear message. | the valid paths are saved with the respective errors for both invalid and empty paths | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-033 | M3 Attributes | FR-018 | Create custom fields of each supported type | Logged in. | 1. Open Attributes > Custom fields 2. Create one field of each available type (text, integer, date, boolean, monetary, URL, select) 3. Assign them to a document | One field per type | Every type is created and can be set on a document. | every type is created successfully | Pass | Medium | Major | EP | Musferah | 2026-10-11
TC-034 | M3 Attributes | FR-019 | Custom field value validation | Custom fields from the previous test exist. | 1. Enter invalid values in the integer, date and URL fields 2. Save 3. Enter valid values and save | Integer: abc, 12.5, -5, 99999999999; Date: 31/02/2026; URL: not a url | Invalid values are rejected with a message; valid values are saved and displayed correctly. | inavlid values are rejected respectively | Pass | High | Major | EP, BVA, EG | Musferah | 2026-10-11
TC-035 | M4 Search & Saved Views | FR-020 | Search for a word present in a document | A document containing the word exists and is indexed. | 1. Type the word into the top search box 2. Press Enter | A word known to be in sample.pdf | The document appears in the results with the match highlighted. | the search shows the word in the document | Pass | High | Major | EP | Azka | 2026-10-11
TC-036 | M4 Search & Saved Views | FR-020 | Search for a word that does not exist | Documents exist. | 1. Search for the nonsense word 2. Check the results | zzzxqv | A clear 'no results' message is shown; no error. | the search with vague words shows no result | Pass | Medium | Minor | EP | Azka | 2026-10-11
TC-037 | M4 Search & Saved Views | FR-020 | Search with empty and special-character queries | Logged in. | 1. Search with each query below 2. Check the page after each search | (empty); (3 spaces); *; %; '; --; <script>alert(1)</script> | No crash or error page; special characters are handled safely and no script runs. | no error with the empty spaces special characters and script dont run | Pass | Medium | Major | EG | Azka | 2026-10-11
TC-038 | M4 Search & Saved Views | FR-021 | Combine tag and correspondent filters | Documents with different tags and correspondents exist. | 1. Filter by tag only 2. Filter by correspondent only 3. Filter by both 4. Filter by neither | Tag: Invoices; Correspondent: ACME | Each combination returns exactly the documents that satisfy all active filters. | each combination returns according to the desired filters | Pass | High | Major | DT | Azka | 2026-10-11
TC-039 | M4 Search & Saved Views | FR-021 | Date range filter boundaries | Documents created on 2026-10-09, 2026-10-10 and 2026-10-11 exist. | 1. Filter from 2026-10-10 to 2026-10-10 2. Filter from 2026-10-11 to 2026-10-09 (start after end) | From/To: 2026-10-10 / 2026-10-10; 2026-10-11 / 2026-10-09 | The single-day filter returns only 10-Oct documents; the reversed range shows no results or a clear message. | the filteration shows the correct results according to the dates | Pass | Medium | Major | BVA | Azka | 2026-10-11
TC-040 | M4 Search & Saved Views | FR-022 | Sort the document list | At least 3 documents exist. | 1. Sort by Created, Added and Title 2. Toggle ascending and descending for each | Sort fields: Created, Added, Title | Order is correct for every field and direction. | order is correct for all types of sorting | Pass | Low | Minor | EP | Azka | 2026-10-11
TC-041 | M4 Search & Saved Views | FR-023 | Create a saved view from a filtered list | Documents with tags exist. | 1. Apply a tag filter and a sort 2. Choose Save as and name the view 3. Open the saved view | View name: Invoices Oct | The view is saved and reproduces the same filters, sort and list when opened. | saved view shows the same filters | Pass | High | Major | EP | Azka | 2026-10-11
TC-042 | M4 Search & Saved Views | FR-023 | Saved view with an empty or duplicate name | Saved view 'Invoices Oct' exists. | 1. Try to save a view with an empty name 2. Try to save another view named Invoices Oct | (empty); Invoices Oct | The empty name is rejected; the duplicate is rejected or handled with a clear message. | the duplicated name shows no feedback | Fail | Low | Minor | EP | Azka | 2026-10-11
TC-043 | M4 Search & Saved Views | FR-024 | Saved view on the dashboard and in the sidebar | A saved view exists. | 1. Turn 'show on dashboard' and 'show in sidebar' on 2. Refresh and check 3. Turn both off 4. Refresh and check | View: Invoices Oct | The view appears or disappears on the dashboard and in the sidebar according to the toggles. | the view appears on the dashboard as expected | Pass | Medium | Minor | ST | Azka | 2026-10-11
TC-044 | M4 Search & Saved Views | FR-025 | Edit and delete a saved view | A saved view exists. | 1. Rename the view and save 2. Delete the view and confirm 3. Check the document list | New name: Invoices Q4 | Rename persists; the deleted view disappears everywhere; documents are unaffected. | the delete and rename shows the desired results | Pass | Medium | Major | EP | Azka | 2026-10-11
TC-045 | M5 Workflows & Matching | FR-027 | Match algorithm 'Any word' | Test PDFs prepared; tag with auto matching available. | 1. Create tag 'Invoices' with algorithm Any word and pattern 'invoice receipt' 2. Upload a PDF containing only the word receipt 3. Check its tags | Pattern: invoice receipt; PDF text: 'receipt' | The document is automatically tagged Invoices. | the document tagged the invoices | Pass | High | Major | DT | Musferah | 2026-10-11
TC-046 | M5 Workflows & Matching | FR-027 | Match algorithm 'All words' | Test PDFs prepared. | 1. Set the tag algorithm to All words with pattern 'invoice paid' 2. Upload a PDF with 'invoice paid' 3. Upload a PDF with only 'invoice' | Pattern: invoice paid | Only the PDF containing both words is tagged. | pdf tagged having both words | Pass | High | Major | DT | Musferah | 2026-10-11
TC-047 | M5 Workflows & Matching | FR-027 | Match algorithm 'Exact' | Test PDFs prepared. | 1. Set the algorithm to Exact with pattern 'Total Due' 2. Upload a PDF with 'Total Due' 3. Upload a PDF with 'Total amount due' | Pattern: Total Due | Only the PDF with the exact phrase is tagged. | document is tagged with the exact phrase | Pass | Medium | Major | DT | Musferah | 2026-10-11
TC-048 | M5 Workflows & Matching | FR-027 | Match algorithm 'Regular expression' (valid) | Test PDFs prepared. | 1. Set the algorithm to Regular expression with the pattern below 2. Upload a PDF containing INV-2026 3. Upload a PDF containing INV-26 | Pattern: ^INV-\d{4}; PDFs: INV-2026, INV-26 | Only the document with a 4-digit number matches and is tagged. | the pdf with the 4 digit number is tagged | Pass | High | Major | BVA, EP | Musferah | 2026-10-11
TC-049 | M5 Workflows & Matching | FR-028 | Invalid regular expression is rejected | Logged in. | 1. Create a tag with algorithm Regular expression 2. Enter the broken pattern 3. Save | Pattern: ([a-z | Save is rejected with a clear validation message; the app stays stable. | the save is rejected with a clear error message of invalid regular expression | Pass | High | Major | EP, EG | Musferah | 2026-10-11
TC-050 | M5 Workflows & Matching | FR-027 | Case-sensitivity option | Test PDFs prepared. | 1. Set pattern INVOICE with case-insensitive ON, upload a PDF containing 'invoice' 2. Set case-insensitive OFF, upload another PDF containing 'invoice' | Pattern: INVOICE; PDF text: invoice | With the option ON the document is tagged; with it OFF the document is not tagged. | pdf is tagged according to the case sensitivity | Pass | Medium | Major | DT | Musferah | 2026-10-11
TC-051 | M5 Workflows & Matching | FR-026 | Workflow with consumption trigger and filename filter | Logged in; tag 'Invoices' exists. | 1. Create a workflow: trigger Consumption, filename filter *invoice*, action Assign tag Invoices 2. Upload invoice_001.pdf 3. Upload notes.pdf | invoice_001.pdf; notes.pdf | Only invoice_001.pdf receives the tag; notes.pdf is untouched. | invoice receives the workflow tag while notes receives nothing | Pass | High | Major | DT, EP | Musferah | 2026-10-12
TC-052 | M5 Workflows & Matching | FR-029 | Disable and re-enable a workflow | The workflow exists. | 1. Disable the workflow 2. Upload invoice_002.pdf 3. Enable the workflow 4. Upload invoice_003.pdf | invoice_002.pdf; invoice_003.pdf | While disabled no tag is applied; after enabling the tag is applied. | the invoice_003 shows the workflow tag while invoice_002 doenst which was uploaded after the disabling of the workflow | Pass | High | Major | ST | Musferah | 2026-10-12
TC-053 | M5 Workflows & Matching | FR-030 | Delete a workflow | The workflow exists. | 1. Delete the workflow and confirm 2. Upload invoice_004.pdf 3. Check earlier documents | invoice_004.pdf | The workflow is removed and no longer triggers; documents processed earlier keep their values. | after deleting the workflow the document isnt tagged however the previous ones remains tagged with the workflow tag | Pass | Medium | Minor | ST | Musferah | 2026-10-12
TC-054 | M6 Trash & Bulk Actions | FR-031 | Restore a document from the trash | A document is in the trash. | 1. Open Trash 2. Select the document and click Restore 3. Check the Documents list | sample.pdf | The document returns to the list with its metadata intact. | the modified date is changed as expected | Pass | High | Major | ST | Azka | 2026-10-12
TC-055 | M6 Trash & Bulk Actions | FR-032 | Permanently delete one document from the trash | Two documents are in the trash. | 1. Open Trash 2. Delete one document permanently and confirm 3. Check Trash and Documents | Any trashed document | A confirmation is shown; the document is gone from Trash and Documents and cannot be restored; the other trashed document is unaffected. | the document is permanently removed | Pass | High | Major | ST | Azka | 2026-10-12
TC-056 | M6 Trash & Bulk Actions | FR-033 | Empty the trash | Several documents are in the trash. | 1. Open Trash 2. Click Empty trash and confirm | n/a | A confirmation is shown; all trashed documents are removed; Trash shows as empty. | all documents are removed | Pass | Medium | Major | ST | Azka | 2026-10-12
TC-057 | M6 Trash & Bulk Actions | FR-034 | Bulk add a tag to selected documents | Five documents exist. | 1. Select 3 of the 5 documents 2. Use the bulk tag action to add a tag 3. Check all 5 documents | Tag: Reviewed; selected: 3 of 5 | Only the 3 selected documents receive the tag. | the documents in bulk are tagged successfully | Pass | High | Major | EP | Azka | 2026-10-12
TC-058 | M6 Trash & Bulk Actions | FR-034 | Bulk action with no documents selected | Documents exist. | 1. Make sure nothing is selected 2. Look for bulk action controls 3. Try to trigger one | Selection: none | Bulk controls are hidden or disabled; no error occurs. | no error occurs | Pass | Low | Trivial | BVA, EG | Azka | 2026-10-12
TC-059 | M6 Trash & Bulk Actions | FR-035 | Bulk delete only the selected documents | Five documents exist. | 1. Select 2 of the 5 documents 2. Click Delete and confirm 3. Check Documents and Trash | Selected: 2 of 5 | The 2 selected documents move to Trash; the other 3 remain. | the 2 documents are in the trash accordingly | Pass | High | Major | EP | Azka | 2026-10-12
TC-060 | M6 Trash & Bulk Actions | FR-035 | Bulk download selected documents | Five documents exist. | 1. Select 3 documents 2. Choose bulk Download 3. Open the downloaded archive | Selected: 3 of 5 | One archive downloads and contains exactly the 3 selected documents; the files open correctly. | the 3 files downloades correctly with the same contents inside as the original | Pass | Medium | Minor | EP | Azka | 2026-10-12
TC-061 | M3 Attributes | FR-018 | Create a Select custom field with no options | Logged in as admin. | 1. Open Attributes > Custom fields > Create 2. Enter the name 3. Choose Data type: Select 4. Add no options 5. Click Save | Name: select; Options: none | A clear validation message asks for at least one option (or Save is disabled until an option exists); the field is not created. | Red 'Error saving field' popup. Details: POST /api/custom_fields/, 400 Bad Request, 'extra_data.select_options must be a valid list' (internal API wording, no user-friendly message). | Fail | Low | Minor | EG | Musferah | 2026-10-11
TC-062 | M3 Attributes | FR-019 | Create a Select custom field with an empty option label | Logged in as admin. | 1. Open Attributes > Custom fields > Create 2. Enter the name 3. Choose Data type: Select 4. Click Add option and leave the label empty 5. Click Save | Name: select; Option label: (empty) | The empty label is rejected with a clear validation message; no server error. | 500 Internal Server Error. The popup Details show a bare HTML 'Server Error (500)' page. A single valid label saves normally. | Fail | Medium | Major | EG, EP | Musferah | 2026-10-11
TC-063 | M3 Attributes | FR-019 | Create a Select custom field with a whitespace-only option label | Logged in as admin. | 1. Open Attributes > Custom fields > Create 2. Enter the name 3. Choose Data type: Select 4. Add an option whose label is only spaces 5. Click Save | Name: select; Option label: (spaces only) | The whitespace-only label is rejected like an empty label. | The field was saved successfully with the whitespace-only option. | Fail | Low | Minor | EG | Musferah | 2026-10-11
TC-064 | M3 Attributes | FR-019 | Create a Select custom field with two options that have the same label | Logged in as admin. | 1. Open Attributes > Custom fields > Create 2. Enter the name 3. Choose Data type: Select 4. Add two options with identical labels 5. Click Save | Name: select; Options: Option A, Option A | Duplicate option labels are rejected (or at least flagged), as duplicate tag names are. | Both options with the same label were accepted and saved. | Fail | Low | Minor | EP | Musferah | 2026-10-11
TC-065 | M3 Attributes | FR-019 | Create a Select custom field with exactly one option | Logged in as admin. | 1. Open Attributes > Custom fields > Create 2. Enter the name 3. Choose Data type: Select 4. Add one option 5. Click Save | Name: select; Options: Option A | A Select field with a single option is accepted. | The field was created successfully with one option. | Pass | Low | Trivial | BVA | Musferah | 2026-10-11
TC-066 | M1 Auth & Users | FR-005 | Restricted user without UISettings permission opens the app | User exists with Document View and Delete only, Admin off, no UISettings permission; documents shared with the user. | 1. Log in as the restricted user 2. Look at the dashboard and the sidebar 3. Open the notifications and expand Details | User: viewdeleteuser; Document: View, Delete; UISettings: none | The user can use the permitted features, or sees a clear message explaining the missing access, with no raw technical error. | Red 'Error loading settings' popup showing /api/ui_settings/ and 403 Forbidden; the sidebar shows only Dashboard and the Documents menu is missing. After UISettings: View is added, the Documents menu and the shared documents appear. | Fail | Medium | Minor | DT | Musferah | 2026-10-11
TC-067 | M4 Search & Saved Views | FR-021 | Custom field filter with an incomplete condition (empty value) | Logged in; documents exist. | 1. Open Documents and click the Custom fields filter 2. Add a condition: field 'date', operator 'Greater than or equal to' 3. Leave the value empty | Field: date; Operator: Greater than or equal to; Value: (empty) | The incomplete condition is ignored, or a clear message asks for a value; the list keeps working. | The list shows 0 documents and a red banner reads 'Error while loading documents: custom_field_query: undefined'. | Fail | Medium | Minor | EG, EP | Azka | 2026-10-11

## DefectLog
Defect ID | Title | Module / Feature | Linked TC ID | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence (EV no.) | Reporter | Date Reported | Notes / Fix info | Impact (used in Top 5 table) | Rank score (automatic)
DEF-001 | Empty option label in a Select custom field causes a 500 Internal Server Error | M3 Attributes | TC-062 | 1. Open Attributes > Custom fields > Create 2. Name: select; Data type: Select 3. Click Add option and leave the label empty 4. Click Save | The empty label is rejected with a clear validation message and the field is not saved. | Red 'Error saving field' popup. Details: POST /api/custom_fields/, status 500 Internal Server Error, with a raw HTML 'Server Error (500)' page. A single valid label saves normally. | Major | Medium | Open | EV-016: Select field with empty option label, popup Details expanded (500 and HTML error page) | Musferah | 2026-10-11 | Reproduced twice. Add the last traceback line from: docker compose logs --tail 60 webserver, and search upstream issues for 'custom field select option 500' before reporting. | A blank option label crashes the server instead of showing a validation message, so the Select field cannot be created and the cause is unclear to the user. | 22.098
DEF-002 | Select custom field with no options shows a raw API error instead of a clear message | M3 Attributes | TC-061 | 1. Open Attributes > Custom fields > Create 2. Name: select; Data type: Select 3. Add no options 4. Click Save | A clear message asks the user to add at least one option (or Save is disabled until an option exists). | Red 'Error saving field' popup. Details: POST /api/custom_fields/, 400 Bad Request, 'extra_data.select_options must be a valid list'. The text is internal API wording. | Minor | Low | Open | EV-022: popup after saving with no options EV-023: popup Details expanded (400) | Musferah | 2026-10-11 | The save is correctly refused; the defect is the unclear message. Related to DEF-001 (same form). | Users see internal API wording instead of a plain instruction to add an option, so the fix is hard to find. | 11.097
DEF-003 | Whitespace-only option label is accepted in a Select custom field | M3 Attributes | TC-063 | 1. Open Attributes > Custom fields > Create 2. Name: select; Data type: Select 3. Add an option whose label is only spaces 4. Click Save | The whitespace-only label is rejected like an empty label. | The field is saved successfully with the whitespace-only option. | Minor | Low | Open | Screenshot still to add: form with the spaces-only option and the success result | Musferah | 2026-10-11 | Inconsistent with DEF-001: an empty label crashes (500) while a spaces-only label is accepted. Screenshot how the blank option looks in the document's dropdown. | A blank-looking option can be saved and shows up as an empty choice on documents, which confuses users picking a value. | 11.096
DEF-004 | Duplicate option labels are accepted in a Select custom field | M3 Attributes | TC-064 | 1. Open Attributes > Custom fields > Create 2. Name: select; Data type: Select 3. Add two options with the same label (Option A, Option A) 4. Click Save | Duplicate option labels are rejected or flagged, as duplicate tag names are. | Both options with the same label are accepted and saved. | Minor | Low | Open | Screenshot still to add: form with the two identical options and the success result | Musferah | 2026-10-11 | Exact duplicate tag names are rejected (TC-026), so this is inconsistent. Screenshot the two identical choices in a document's dropdown. | Identical options cannot be told apart, so users can pick the wrong value and the stored data becomes ambiguous. | 11.095
DEF-005 | Restricted user sees a raw 403 'Error loading settings' popup and an empty menu | M1 Auth & Users | TC-066 | 1. As admin, create a user with Document View and Delete only; Admin off; no UISettings permission 2. Share the documents with that user 3. Log in as that user | The user can use the permitted features, or sees a clear message explaining the missing access, with no raw technical error. | Red 'Error loading settings' popup: /api/ui_settings/ 403 Forbidden. The sidebar shows only Dashboard and the Documents menu is missing. After UISettings: View is added, the menu and documents appear. | Minor | Medium | Open | EV-024: permissions page (no UISettings) EV-025: 403 popup EV-026: dashboard after UISettings added | Musferah | 2026-10-11 | VERIFY BEFORE SUBMITTING: search the Paperless docs and GitHub discussions for 'UISettings' and 'ui_settings 403'. If this behaviour is documented as required, change Status to Rejected and move it to the observations section. | A user with limited permissions sees a raw error and an almost empty menu, with no explanation of what is missing. | 12.094
DEF-006 | Saving a view with a duplicate name shows no message and no feedback | M4 Search & Saved Views | TC-042 | 1. Open Documents and apply a tag filter 2. Open Views > Save as, enter a name and click Save 3. Apply the same filter again and open Save as 4. Enter the same name and click Save | A clear message says the name already exists, or the Save button is disabled. | Clicking Save gives no feedback: no error message, no confirmation, and the Save button is not disabled. | Minor | Low | Open | EV-027: Save current view dialog with the duplicate name | Azka | 2026-10-11 | Open the Views list after saving and note whether a second view with the same name was created. | Users get no feedback when a view cannot be saved, so they do not know whether it worked. | 11.092
DEF-007 | Custom field filter with an empty value shows a raw error ('custom_field_query: undefined') | M4 Search & Saved Views | TC-067 | 1. Open Documents and click the Custom fields filter 2. Add a condition: field 'date', operator 'Greater than or equal to' 3. Leave the value empty | The incomplete condition is ignored, or a clear message asks for a value; the document list keeps working. | The list shows 0 documents and a red banner reads 'Error while loading documents: custom_field_query: undefined'. | Minor | Medium | Open | EV-028: filter condition with empty value and the error banner | Azka | 2026-10-11 | Seen during testing; reproduce once more before the viva. Search upstream issues for 'custom_field_query undefined'. | An incomplete filter breaks the document list with an unreadable error until the filter is reset. | 12.091

## Defect_Summary
Defect Summary - Paperless-ngx v3.3.0
All figures are formulas that read the DefectLog sheet, so they update when you add or change a defect.
Total defects found | 7 |  |  |  |  | The Top 5 most critical defects are on the Top5_Defects sheet.
Defects by severity
Severity | Count | % of total
Critical | 0 | 0%
Major | 1 | 14.29%
Minor | 6 | 85.71%
Trivial | 0 | 0%
Total | 7 | 100%
Defects by priority
Priority | Count | % of total
High | 0 | 0%
Medium | 3 | 42.86%
Low | 4 | 57.14%
Total | 7 | 100%
Defects by status
Status | Count | % of total
Open | 7 | 100%
Fixed | 0 | 0%
Closed | 0 | 0%
Rejected | 0 | 0%
Deferred | 0 | 0%
Total | 7 | 100%
Defects by module
Module | Total | Critical | Major | Minor | Trivial
M1 Auth & Users | 1 | 0 | 0 | 1 | 0
M2 Documents | 0 | 0 | 0 | 0 | 0
M3 Attributes | 4 | 0 | 1 | 3 | 0
M4 Search & Saved Views | 2 | 0 | 0 | 2 | 0
M5 Workflows & Matching | 0 | 0 | 0 | 0 | 0
M6 Trash & Bulk Actions | 0 | 0 | 0 | 0 | 0
Total | 7 | 0 | 1 | 6 | 0

## Summary
Test Execution Summary - Paperless-ngx v3.3.0
Metric | Value
Total test cases designed | 67
Test cases executed (Passed + Failed) | 66
Passed | 59
Failed | 7
Blocked | 1
Not executed | 0
Pass percentage (Passed / Executed) | 89.39%
Execution effort (hours) - enter total | 15
Module-wise breakdown
Module | Total | Passed | Failed | Blocked | Not Executed | Defects
M1 Auth & Users | 12 | 11 | 1 | 0 | 0 | 1
M2 Documents | 12 | 11 | 0 | 1 | 0 | 0
M3 Attributes | 16 | 12 | 4 | 0 | 0 | 4
M4 Search & Saved Views | 11 | 9 | 2 | 0 | 0 | 2
M5 Workflows & Matching | 9 | 9 | 0 | 0 | 0 | 0
M6 Trash & Bulk Actions | 7 | 7 | 0 | 0 | 0 | 0
Total | 67 | 59 | 7 | 1 | 0 | 7
Defect summary
Total defects | 7
Severity | Count |  | Priority | Count |  | Status | Count
Critical | 0 |  | High | 0 |  | Open | 7
Major | 1 |  | Medium | 3 |  | Fixed | 0
Minor | 6 |  | Low | 4 |  | Closed | 0
Trivial | 0 |  |  |  |  | Rejected | 0
[6 empty] | Deferred | 0
Test design technique coverage (a test may use more than one technique)
Technique | Test cases
EP | 38
BVA | 12
DT | 8
ST | 9
EG | 13

## Top5_Defects
Top 5 Most Critical Defects - Paperless-ngx v3.3.0
Ranking rule: higher severity first (Critical, Major, Minor, Trivial), then higher priority (High, Medium, Low), then the earlier defect ID. Updates automatically from the DefectLog sheet.
Rank | Defect ID | Title | Module | Severity | Priority | Impact
1 | DEF-001 | Empty option label in a Select custom field causes a 500 Internal Server Error | M3 Attributes | Major | Medium | A blank option label crashes the server instead of showing a validation message, so the Select field cannot be created and the cause is unclear to the user.
2 | DEF-005 | Restricted user sees a raw 403 'Error loading settings' popup and an empty menu | M1 Auth & Users | Minor | Medium | A user with limited permissions sees a raw error and an almost empty menu, with no explanation of what is missing.
3 | DEF-007 | Custom field filter with an empty value shows a raw error ('custom_field_query: undefined') | M4 Search & Saved Views | Minor | Medium | An incomplete filter breaks the document list with an unreadable error until the filter is reset.
4 | DEF-002 | Select custom field with no options shows a raw API error instead of a clear message | M3 Attributes | Minor | Low | Users see internal API wording instead of a plain instruction to add an option, so the fix is hard to find.
5 | DEF-003 | Whitespace-only option label is accepted in a Select custom field | M3 Attributes | Minor | Low | A blank-looking option can be saved and shows up as an empty choice on documents, which confuses users picking a value.